## sprint-planning
Sprint Planning
Sprint 1
Name | Person | Status | Priority | Estimation | Epics | Description | Creation Log
API study |  | Done | High | 5 | general |  | 2018-11-14
Food API - study | Abdul | Done | Medium | 3 | api |  | 2018-11-14
DB study | José Alfonzo | Done | Medium | 3 | general |  | 2018-11-14
Bot set up |  | Done | High | 5 | general |  | 2018-11-14
Sleep API - study | sofia alexandra valente cirne | Dev | Medium | 3 | api |  | sofia alexandra valente cirne 2018-11-20
Git set up | sofia alexandra valente cirne | Done | High | 5 | general |  | sofia alexandra valente cirne 2018-11-20
menu set up - main file | sofia alexandra valente cirne | Dev | High | 5 | general |  | sofia alexandra valente cirne 2018-11-21
account |  | Done | High |  |  |  | João Dantas 2018-11-22
29
Sprint 2
Name | Person | Status | Priority | Estimation | Epics | Description | Creation Log
food api installation | Abdul | Done | Medium | 2 | infra |  | 2018-11-14
database setup | José Alfonzo | Dev | High |  |  |  | José Alfonzo 2018-11-21
code editing from terminal to discord | José Alfonzo | Dev | High |  |  |  | José Alfonzo 2018-11-21
sleep API - search | sofia alexandra valente cirne | Done | Medium | 2 | api |  | sofia alexandra valente cirne 2018-11-21
fixing errors | sofia alexandra valente cirne | Done | High |  |  |  | sofia alexandra valente cirne 2018-11-21
Sleep Graph |  | Done | High |  |  | Just need to correct it, but the code is all there i think | João Dantas 2018-11-22
Exercise Graph |  | Done | High |  |  | Just need to correct it, but the code is all there i think | João Dantas 2018-11-22
Food Graph |  | Done | High |  |  | Just need to correct it, but the code is all there i think | João Dantas 2018-11-22
Playtime Graph |  | Done | High |  |  | Just need to correct it, but the code is all there i think | João Dantas 2018-11-22
4
Sprint 3
Name | Person | Status | Priority | Estimation | Epics | Description | Creation Log
LOL API - URL | sofia alexandra valente cirne | Done | Medium | 4 |  |  | sofia alexandra valente cirne 2018-11-21
Unit Testing - Game_LOL | sofia alexandra valente cirne | Dev | High | 5 |  |  | sofia alexandra valente cirne 2018-11-21
ChatBot Discord Test - Wally | sofia alexandra valente cirne | Done | Low | 2 |  |  | sofia alexandra valente cirne 2018-11-21
Account fixes |  | Dev | Medium |  |  |  | João Dantas 2018-11-22
youtube api |  | Dev | High | 2 |  |  | Abdul 2018-11-23
13
Sprint 4
Name | Person | Status | Priority | Estimation | Epics | Description | Creation Log
uni Testing - Game_LOL | sofia alexandra valente cirne | Dev | High |  |  |  | sofia alexandra valente cirne 2018-11-21
sleep.py | sofia alexandra valente cirne | Done | Medium |  |  |  | sofia alexandra valente cirne 2018-11-21
main file - Menu | sofia alexandra valente cirne | Dev | High |  |  |  | sofia alexandra valente cirne 2018-11-21
0
Backlog
Name | Person | Status | Priority | Estimation | Epics | Description | Creation Log